## Inputs for CF
AC Capacity | 325 | MW
Inverter Capacity | 390 | MW
DC Capacity | 487.5 | MWp
Items | Total Cost | Total Cost in Crores | % of Cost | IDC & Risk Loading | Spares & Freight Loading | Total cost with IDC Loading | Total Sales | % of Sales/invoice | Total Invoice | Client Payment Terms | % of CV | Invoice Value | Supply | Erection | Civil | Check
Cell | 0.20513 | 100 | 10% | 7.5269 |  | 107.5269 | 119.4743 | 10.75% |  | Advance Payment | 15% | 3.4188e-08 | 116.4875 |  |  | 116.4875
BCD | 0.12308 | 60 | 6% | 4.5161 |  | 64.5161 | 71.6846 | 6.452%
Cell Tolling - Module | 0.82051 | 400 | 40% | 30.1075 |  | 430.1075 | 477.8973 | 43.01% | 669.0562 | Studies, PO Placement |  | 0 | 0 | 0 | 0 | 0
Inverter | 0.082051 | 40 | 4% | 3.0108 | 0 | 43.0108 | 47.7897 | 4.301% | 47.7897 | Despatch | 100% | 2.2792e-07 | 776.583 |  |  | 776.583
MMS - Tracker | 0.12308 | 60 | 6% | 4.5161 | 0 | 64.5161 | 71.6846 | 6.452% | 71.6846 | Civil Works | 15% | 3.4188e-08 |  |  | 4.4444e-08 | 1.0256e-08
Power Transformer | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0
Cables | 0.082051 | 40 | 4% | 3.0108 | 0 | 43.0108 | 47.7897 | 4.301% | 47.7897 | Installation |  | 0 |  | 0 |  | 0
IDT | 0.061538 | 30 | 3% | 2.2581 | 0 | 32.2581 | 35.8423 | 3.226% | 35.8423 | Commissioning (BOS contractor can commission multiple blocks simultaneously) |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0 |  | 0 | 0 | 0% | 0 | Completion of PR test, all punch points, As built documentation and Handover of the complete project & submission of PBG for defect liability period |  | 0 | 0 | 0 | 0 | 0
Other Supply | 0.1641 | 80 | 8% | 6.0215 | 0 | 86.0215 | 95.5795 | 8.602% | 95.5795 | Total | 130% | 2.963e-07 | 893.0705 | 0 | 4.4444e-08 | 893.0705
| 0 | 0 | 0% | 0 |  | 0 | 0 | 0% | 0 |  |  |  | 3014112903.2258 | 0% | 15%
Erection | 0.020513 | 10 | 1% | 0.75269 |  | 10.7527 | 11.9474 | 1.075% | 11.9474
Civil | 0.22564 | 110 | 11% | 8.2796 |  | 118.2796 | 131.4217 | 11.83% | 131.4217
Power Evacuation | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0
Mandatory Spares & Freight | 0 | 0 | 0%
IDC and R&C | 0.14359 | 70 | 7%
Total | 2.0513 | 1000 | 100% | 70 | 0 | 1000 | 1111.1111 | 100% | 1111.1111
GM% | 10% | 10%
Sales | 2.2792 | 1111.1111
Gross Margin | 0.22792 | 111.1111

## Cashflow
[19 empty] | Comm | Compl |  |  | PG Test
| Outflow | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
| Items | Value | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | Total | Check | Payment Terms/Assumptions | Delivery No of Months/Lots
| Cell | 100 | 2025-05-01: 33.3333; 2025-07-01: 33.3333; 2025-09-01: 33.3333 | 100 | 0 | 100% Credit period - 90 days | 3
| BCD | 60 | 2025-02-01: 20; 2025-04-01: 20; 2025-06-01: 20 | 60 | 0 | Immediate after receipt at port | 3
| Cell Tolling - Module | 400 | 2025-10-01: 45.7143; 2025-11-01: 57.1429; 2025-12-01: 57.1429; 2026-01-01: 57.1429; 2026-02-01: 57.1429; 2026-03-01: 57.1429; 2026-04-01: 57.1429; 2026-05-01: 8.5714; 2026-06-01: 2.8571 | 400 | 0 | 100% Credit period - 180 days VFS | 7
| Inverter | 40 | 2025-06-01: 8; 2025-07-01: 8; 2025-08-01: 8; 2025-09-01: 8; 2025-10-01: 8 | 40 | 0 | 10% advance, 90% Credit period - 90 days | 5
| MMS - Tracker | 60 | 2025-03-01: 10; 2025-04-01: 10; 2025-05-01: 10; 2025-06-01: 10; 2025-07-01: 10; 2025-08-01: 10 | 60 | 0 | 100% Credit period - 60 days | 6
| Power Transformer | 0 | [41 empty] | 0 | 0 | 100% Credit period - 90 days | 2
| Cables | 40 | 2025-05-01: 5.7143; 2025-06-01: 5.7143; 2025-07-01: 5.7143; 2025-08-01: 5.7143; 2025-09-01: 5.7143; 2025-10-01: 5.7143; 2025-11-01: 5.7143 | 40 | 0 | 100% Credit period - 90 days | 7
| IDT | 30 | 2025-06-01: 6; 2025-07-01: 6; 2025-08-01: 6; 2025-09-01: 6; 2025-10-01: 6 | 30 | 0 | 100% Credit period - 90 days | 5
| 0 | 0 | [41 empty] | 0 | 0 | 100% Credit period - 60 days | 3
| Other Supply | 80 | 2025-02-01: 10; 2025-03-01: 10; 2025-04-01: 10; 2025-05-01: 10; 2025-06-01: 10; 2025-07-01: 10; 2025-08-01: 10; 2025-09-01: 10 | 80 | 0 | 100% Credit period - 45 days | 8
| 0 | 0 | 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0; 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0; 2027-06-01: 0 | 0 | 0 | 100% Credit period - 60 days | 17
| Erection | 10 | 2025-03-01: 0.5; 2025-04-01: 0.5; 2025-05-01: 0.9; 2025-06-01: 1.4; 2025-07-01: 1.4; 2025-08-01: 1.4; 2025-09-01: 0.9; 2025-10-01: 1; 2025-11-01: 0.8; 2025-12-01: 0.5; 2026-01-01: 0.5; 2026-02-01: 0.2 | 10 | 0 | 100% Credit period - 45 days | 11
| Civil | 110 | 2025-01-01: 2.2; 2025-02-01: 6.6; 2025-03-01: 8.8; 2025-04-01: 13.2; 2025-05-01: 14.3; 2025-06-01: 14.3; 2025-07-01: 14.3; 2025-08-01: 9.9; 2025-09-01: 9.9; 2025-10-01: 5.5; 2025-11-01: 5.5; 2025-12-01: 2.2; 2026-01-01: 2.2; 2026-02-01: 1.1 | 110 | 0 | 100% Credit period - 45 days | 13
| Power Evacuation | 0 | 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0 | 0 | 0 | 100% Credit period - 45 days | 7
| Mandatory Spares & Freight | 0 | 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0 | 0 | 0 | 100% Credit period - 60 days | 3
| IDC and R&C | 70 | 2024-09-01: 0.7; 2024-10-01: 0.7; 2024-11-01: 0.7; 2024-12-01: 1.4; 2025-01-01: 2.1; 2025-02-01: 3.5; 2025-03-01: 4.9; 2025-04-01: 4.9; 2025-05-01: 4.9; 2025-06-01: 5.25; 2025-07-01: 5.25; 2025-08-01: 6.3; 2025-09-01: 6.3; 2025-10-01: 6.3; 2025-11-01: 5.95; 2025-12-01: 4.9; 2026-01-01: 1.4; 2026-02-01: 1.4; 2026-03-01: 1.75; 2026-04-01: 1.4 | 70 | 0
| Total - Outflow | 1000 | 0.7 | 0.7 | 0.7 | 1.4 | 4.3 | 40.1 | 34.2 | 58.6 | 79.1476 | 80.6643 | 93.9976 | 57.3143 | 80.1476 | 78.2286 | 75.1071 | 64.7429 | 61.2429 | 59.8429 | 58.8929 | 58.5429 | 8.5714 | 2.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0
|  |  | 0.07% | 0.14% | 0.21% | 0.35% | 0.78% | 4.79% | 8.21% | 14.07% | 21.98% | 30.05% | 39.45% | 45.18% | 53.2% | 61.02% | 68.53% | 75.01% | 81.13% | 87.11% | 93% | 98.86% | 99.71% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Inflow | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
| Items | Value | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | Total | Check | Client Payment Terms ( Credit Period : 30 days) | % | Value
| Cell | 0 | 2024-09-01: 0 | 0 | 0 | Supply
| BCD | 0 | 2024-09-01: 0 | 0
| Cell Tolling - Module | 669.0562 | 2024-09-01: 100.3584; 2025-06-01: 53.5245; 2025-07-01: 66.9056; 2025-08-01: 66.9056; 2025-09-01: 66.9056; 2025-10-01: 66.9056; 2025-11-01: 66.9056; 2025-12-01: 66.9056; 2026-01-01: 10.0358; 2026-02-01: 3.3453; 2026-03-01: 16.7264; 2026-04-01: 16.7264; 2026-07-01: 66.9056; 2027-11-01: 0 | 669.0562 | 0 | Advance Payment | 15% | 145.1613
| Inverter | 47.7897 | 2024-09-01: 7.1685; 2025-05-01: 6.6906; 2025-06-01: 6.6906; 2025-07-01: 6.6906; 2025-08-01: 6.6906; 2025-09-01: 6.6906; 2026-03-01: 1.1947; 2026-04-01: 1.1947; 2026-07-01: 4.779; 2027-11-01: 0 | 47.7897 | 0 | Against dispatch of Material from Manufacturer’s work | 55% | 532.2581
| MMS - Tracker | 71.6846 | 2024-09-01: 10.7527; 2025-03-01: 8.3632; 2025-04-01: 8.3632; 2025-05-01: 8.3632; 2025-06-01: 8.3632; 2025-07-01: 8.3632; 2025-08-01: 8.3632; 2026-03-01: 1.7921; 2026-04-01: 1.7921; 2026-07-01: 7.1685; 2027-11-01: 0 | 71.6846 | 0 | Upon receipt of Supply of Material/Equipment at site & Acceptance thereof. | 15% | 145.1613
| Power Transformer | 0 | 2024-09-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-07-01: 0; 2027-11-01: 0 | 0 | 0 | Upon Commissioning | 2.5% | 24.1935
| Cables | 47.7897 | 2024-09-01: 7.1685; 2025-04-01: 4.779; 2025-05-01: 4.779; 2025-06-01: 4.779; 2025-07-01: 4.779; 2025-08-01: 4.779; 2025-09-01: 4.779; 2025-10-01: 4.779; 2026-03-01: 1.1947; 2026-04-01: 1.1947; 2026-07-01: 4.779; 2027-11-01: 0 | 47.7897 | 0 | Upon Completion of Facilities | 2.5% | 24.1935
| IDT | 35.8423 | 2024-09-01: 5.3763; 2025-05-01: 5.0179; 2025-06-01: 5.0179; 2025-07-01: 5.0179; 2025-08-01: 5.0179; 2025-09-01: 5.0179; 2026-03-01: 0.89606; 2026-04-01: 0.89606; 2026-07-01: 3.5842; 2027-11-01: 0 | 35.8423 | 0 | Upon successful completion of PG Test | 10% | 96.7742
| 0 | 0 | 2024-09-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-07-01: 0 | 0 | 0 | Services
| Other Supply | 95.5795 | 2024-09-01: 14.3369; 2025-03-01: 8.3632; 2025-04-01: 8.3632; 2025-05-01: 8.3632; 2025-06-01: 8.3632; 2025-07-01: 8.3632; 2025-08-01: 8.3632; 2025-09-01: 8.3632; 2025-10-01: 8.3632; 2026-03-01: 2.3895; 2026-04-01: 2.3895; 2026-07-01: 9.5579; 2027-11-01: 0 | 95.5795 | 0 | Interest bearing advance payment | 10% | 14.3369
| 0 | 0 | 2024-09-01: 0; 2025-10-01: 0 | 0 | 0 | On pro-rata basis against Completion and certification | 75% | 107.5269
19% | Erection | 11.9474 | 2024-09-01: 0; 2025-04-01: 0.50575; 2025-05-01: 0.50575; 2025-06-01: 0.91035; 2025-07-01: 1.4161; 2025-08-01: 1.4161; 2025-09-01: 1.4161; 2025-10-01: 0.91035; 2025-11-01: 1.0115; 2025-12-01: 0.8092; 2026-01-01: 0.50575; 2026-02-01: 0.50575; 2026-03-01: 0.2023; 2026-04-01: 0.29869; 2026-05-01: 0.29869; 2026-06-01: 0; 2026-07-01: 1.1947 | 11.9071 | -0.040317 | Upon Commissioning | 2.5% | 3.5842
19% | Civil | 131.4217 | 2025-02-01: 2.2253; 2025-03-01: 6.6759; 2025-04-01: 8.9012; 2025-05-01: 13.3518; 2025-06-01: 14.4644; 2025-07-01: 14.4644; 2025-08-01: 14.4644; 2025-09-01: 10.0138; 2025-10-01: 10.0138; 2025-11-01: 5.5633; 2025-12-01: 5.5633; 2026-01-01: 2.2253; 2026-02-01: 2.2253; 2026-03-01: 1.1126; 2026-04-01: 3.2855; 2026-05-01: 3.2855; 2026-07-01: 13.1422 | 130.9783 | -0.44348 | Upon Completion of Facilities | 2.5% | 3.5842
| Power Evacuation | 0 | 2024-09-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-07-01: 0; 2027-11-01: 0 | 0 | 0 | Upon successful completion of PG Test | 10% | 14.3369
| Key equipment erection | [42 empty] | 0 | 0 | bar: 2027-07-01
| Mandatory Spares & Freight | 0 | [41 empty] | 0 | 0 | bar: 2027-07-01
| IDC and R&C | 0 | [41 empty] | 0 | 0 | bar: 2027-07-01
| Total - Inflow | 1111.1111 | 145.1613 | 0 | 0 | 0 | 0 | 2.2253 | 23.4023 | 30.9123 | 47.0714 | 102.1132 | 116 | 116 | 103.1862 | 90.972 | 73.4804 | 73.2781 | 12.7669 | 6.0763 | 25.5085 | 27.7778 | 3.5842 | 0 | 111.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110.6273 | -0.4838 | Total | 200% | 1111.1111
|  |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.26% | 15.37% | 18.15% | 22.39% | 31.58% | 42.02% | 52.46% | 61.75% | 69.93% | 76.55% | 83.14% | 84.29% | 84.84% | 87.13% | 89.63% | 89.96% | 89.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96%
| Cum. Cash Inflow | 1111.1111 | 145.1613 | 145.1613 | 145.1613 | 145.1613 | 145.1613 | 147.3866 | 170.7889 | 201.7012 | 248.7726 | 350.8858 | 466.8858 | 582.8858 | 686.0721 | 777.044 | 850.5244 | 923.8025 | 936.5694 | 942.6457 | 968.1542 | 995.932 | 999.5162 | 999.5162 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273
| Cum. Cash Outflow | 1000 | 0.7 | 1.4 | 2.1 | 3.5 | 7.8 | 47.9 | 82.1 | 140.7 | 219.8476 | 300.5119 | 394.5095 | 451.8238 | 531.9714 | 610.2 | 685.3071 | 750.05 | 811.2929 | 871.1357 | 930.0286 | 988.5714 | 997.1429 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
| Net Cashflow | 111.1111 | 144.4613 | 143.7613 | 143.0613 | 141.6613 | 137.3613 | 99.4866 | 88.6889 | 61.0012 | 28.925 | 50.3739 | 72.3763 | 131.062 | 154.1006 | 166.844 | 165.2173 | 173.7525 | 125.2765 | 71.51 | 38.1256 | 7.3605 | 2.3733 | -0.4838 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273
[14 empty] | 0% | 0% | 0% | 0% | 0%
Invoice
| Cell Tolling - Module | 267.6225 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 76.4636; 2025-05-01: 95.5795; 2025-06-01: 95.5795
| Inverter | 38.2318 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 9.5579; 2025-04-01: 9.5579; 2025-05-01: 9.5579; 2025-06-01: 9.5579
| MMS - Tracker | 71.6846 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 11.9474; 2025-02-01: 11.9474; 2025-03-01: 11.9474; 2025-04-01: 11.9474; 2025-05-01: 11.9474; 2025-06-01: 11.9474
| Power Transformer | 0 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0
| Cables | 34.1355 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 6.8271; 2025-03-01: 6.8271; 2025-04-01: 6.8271; 2025-05-01: 6.8271; 2025-06-01: 6.8271
| IDT | 28.6738 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 7.1685; 2025-04-01: 7.1685; 2025-05-01: 7.1685; 2025-06-01: 7.1685
| 0 | 0 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0
| Other Supply | 71.6846 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 11.9474; 2025-02-01: 11.9474; 2025-03-01: 11.9474; 2025-04-01: 11.9474; 2025-05-01: 11.9474; 2025-06-01: 11.9474
| Power Evacuation | 0 | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0
| Subtotal |  |  | 0 | 0 | 0 | 23.8949 | 30.722 | 47.4484 | 123.9119 | 143.0278 | 143.0278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Adjusted |  | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 3.5842; 2025-02-01: 4.6083; 2025-03-01: 7.1173; 2025-04-01: 18.5868; 2025-05-01: 21.4542; 2025-06-01: 21.4542; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 76.8049
|  |  |  | 0 | 0% | 0% | 2.469% | 5.644% | 10.55% | 23.35% | 38.13% | 52.91% | 52.91% | 52.91%
|  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | [6 empty] | M20 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33
|  | Cum. Cash Inflow | 145.1613 | 145.1613 | 145.1613 | 145.1613 | 145.1613 | 147.3866 | 170.7889 | 201.7012 | 248.7726 | 350.8858 | 466.8858 | 582.8858 | 686.0721 | 777.044 | 850.5244 | 923.8025 | 936.5694 | 942.6457 | 968.1542 | [6 empty] | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273 | 1110.6273
|  | Cum. Cash Outflow | 0.7 | 1.4 | 2.1 | 3.5 | 7.8 | 47.9 | 82.1 | 140.7 | 219.8476 | 300.5119 | 394.5095 | 451.8238 | 531.9714 | 610.2 | 685.3071 | 750.05 | 811.2929 | 871.1357 | 930.0286 | [6 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
|  | Net Cashflow | 144.4613 | 143.7613 | 143.0613 | 141.6613 | 137.3613 | 99.4866 | 88.6889 | 61.0012 | 28.925 | 50.3739 | 72.3763 | 131.062 | 154.1006 | 166.844 | 165.2173 | 173.7525 | 125.2765 | 71.51 | 38.1256 | [6 empty] | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273 | 110.6273
19.47%
Note on V28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why it is after 2 months?